## Sheet1
Application | Headline | No. | Objective | Type | Proposed solution | Initiation Date | Estimated completion date | Completion date | Current status | Assigned to | Result
System admin | Custom responspilty | 1 | Unauthorized users may access specific data, and we need to prevent that. | New feature | Creating custom responsibilities with a specific request group for each user. | 2025-01-16 | 2025-01-17 | 2025-01-17 | Closed | Farag | Completed
System admin | Custom menu | 2 | There's a need to prevent some employess from using specific fucntions/sub menus (eg, setup sub menu) | New feature | Making custom menus for each employee. | 2025-01-16 | 2025-01-17 | 2025-01-17 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
System admin | Charts of account | 3 | The organization currently operates with multiple disjointed accounting structures across departments, leading to Inconsistent financial reporting. | New feature | Design and implement a centralized and scalable Chart of Accounts. | 2025-01-20 | 2025-01-21 | 2025-01-21 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
System admin | Short hand allias | 4 | There's a need to prevent entering miscombined account numbers upon making a transaction. | New feature | Implement a shorthand alias. | 2025-01-20 | 2025-01-21 | 2025-01-21 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Item master | 5 | There's a need for a unified data source. | New feature | Creating One Item master for both branches. | 2025-01-16 | 2025-01-17 | 2025-01-17 | Closed | Farag | Completed
Inventory | Item status | 6 | There's a need to phase out items that are no longer in demand ,eg."PC-006" | New feature | The item statutes will be set to (phase out). | 2025-01-20 | 2025-01-21 | 2025-01-21 | Closed | Ashraf | Completed
Inventory | Set (costing method) | 7 | Matching the costing method of the Pixel Core stock management units "Standard" with the organization. | New feature | In the inventory parameters the Costing method will be set to (Standard). | 2025-01-20 | 2025-01-21 | 2025-01-21 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completed
Inventory | Min/Max | 8 | There's a need to ensure the warehouses don't face a supply shortage. | New feature | Automate replenishment by enabling MinMax planning on the retail. | 2025-01-23 | 2025-01-24 | 2025-01-24 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completed
Inventory | Lot/serial control | 9 | There's a Need to ensure traceability for batch tracking and compliance. | New feature | Enable Lot & Serial Control to track product movements. | 2025-01-24 | 2025-01-25 | 2025-01-25 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Sub-inventory restriction | 10 | There's a Need to ensure some specific items enter a custom and special sub-inventory (for custom storing purposes). | New feature | Apply Sub-Inventory Restrictions based on user roles and permissions. | 2025-01-26 | 2025-01-27 | 2025-01-27 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Internal requisition | 11 | There's a need to transfer stock among warehouses. | New feature | Use Internal requisitions to improve stock transfers. | 2025-01-28 | 2025-01-29 | 2025-01-29 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Physical inventory | 12 | There's a need to ensure inventory accuracy by comparing system records with actual stock. | New feature | Use Physical Inventory so we can manage stock count adjustments and improve inventory accuracy. | 2025-01-29 | 2025-01-30 | 2025-01-30 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Reciept routing | 13 | There's a need to prevent imported items from entering Suez Inventories before inspection. | New feature | Set the receipt routing for the Suez district to inspection required in the Suez district receiving options. | 2025-01-30 | 2025-01-31 | 2025-01-31 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Custom transaction | 14 | Items moving from the Receiving Sub-inventory to the Stores Sub-inventory must first pass Quality Inspection. | New feature | A custom transaction ensures that only quality-approved items can be transferred. | 2025-02-01 | 2025-02-02 | 2025-02-02 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Internal requisition | 15 | There's a need to provide our employees with laptops for work purposes. | New feature | Use an internal requisition. | 2025-02-05 | 2025-02-06 | 2025-02-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Miscellaneous transactions | 16 | There's a need to adjust some records related to inventory. | New feature | Use miscellaneous transactions for adjustments. | 2025-02-06 | 2025-02-07 | 2025-02-07 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Item template | 17 | There's a need to have a template for the items with the same attributes to reduce human error, enhance and shorten the process of creation of an item like ( finished goods: stockable, shippable, Raw Materials: stockable, not shippable) | New feature | Create and use item templates to speed up item creation, ensure consistency, reduce errors and improve efficiency. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 18 | The Giza branch can only request for qutuotions and isn't permitted to make POs | New feature | Set the chech box (RFQ Only) in finacial options to allowed. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Receiving options | 19 | There's a need to inspect returned items before entering the Inventories. | New feature | Set RMA routing for the inventory organizations to inspection required in the receiving options. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory |  | 20 | The goods should not be delivered earlier or later than one week from the scheduled receipt date, to ensure accuracy. | New feature | In the receiving options, the Receipt date early and Receipt date late will both be set to 7, and the Receipt days Exceed-action will be set to reject. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory |  | 21 | Our procedures do not allow for over-receipting at the time of delivery. | New feature | In the recieving options the Over Reciept tolerance will be set to 0 % and the Over Receipt action will be set to reject. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory |  | 22 | In certain cases, there's a need to receive some items before making POs. | New feature | The receiving options allow unordered receipts. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory |  | 23 | It is essential to check the serial number of any item returned by a customer to ensure proper validation. | New feature | In the receiving options, allow "validate Serial Numbers on 'RMA Receipts'. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory |  | 24 | Lot number verification is required for all items returned by customers. | New feature | In the receiving options, "Validate Lots on RMA Receipts" will be set to "Restricted with warning". | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Custody | 25 | There's a need to define an area for returned Custody that had been issued for the employees before. | New feature | Creating a (Receipt of custody) Locator. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Custody | 26 | There's a need to define a specific reason for the (Custody Receipt) Transactions. | New feature | Create a custom reason called (Custody Receipt). | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Custody | 27 | There's a need to transact the returned custody to the (Receipt of custody) Locator. | New feature | Creating a custom transaction called (Custody Receipt). | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Revision control | 28 | Some items share every feature, including the cost, but they are different colors, creating a separate item code for them is time-consuming. | New feature | Enable Revision Control on these items. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Specify (locators) | 29 | There's a need to define an area for returned items. | New feature | Creating (Returned Items) Locator in all 4 sub-inventories (2 retailers- 2 Warehouses). | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Unit of measure | 30 | There's a need to define custom units for certain packages and accessories. | New feature | Creating a custom unit of measure and conversions (P.C.E). | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | User item type | 31 | Some items are used for promotional purposes, so we need them to be grouped as promotional items. | New feature | In item attributes, set User item type to (PROMOTIONAL_ITEM). | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Lot divisable | 32 | There's a need to receive certain lots into 2 separate warehouses. | New feature | In item inventory attribute group, allow "Lot Divisible". | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Defective items | 33 | There's a need to make it easier to separate and track defective items from good stock. | New feature | Set up a specific locator in the system for defective items, so users know exactly where to store them and can easily manage them during inspections or returns
Inventory | Shipping network | 34 | There's a need to transfer goods from the Suez district inventory organization to the rest of the inventory organizations. | New feature | Set shipping inventories from the Suez district inventory organization to the rest of the inventory organizations. | 2025-02-07 | 2025-02-08 | 2025-02-08 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Inventory | Material status | 35 | There's a need to restrict transactions upon making a physical count to prevent interference. | New feature | Create and set up a new Material status named "Physical Count Adjustments" that will restrict any transaction. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Price tolerance % | 36 | There's a need to allow only slight price changes when receiving or invoicing (about 3%). | New feature | Set price tolerance in purchasing options to 3% and enable Enforce Price Tolerance options. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 37 | There's a need to enforce suppliers to deliver in full lot quantities. | New feature | Set Enforce Full Lot Quantity to Mandatory. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Receipt close point | 38 | Automatically close POs once the the items are received. | New feature | Set the Receipt Close Point to (Received). | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Purcahsing options | 39 | There's a need to enable the automatic cancellation of requisitions that are no longer required. | New feature | Set Cancel Requisitions to (Always). | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 40 | Alert users if a Blanket Purchase Agreement (BPA) already exists. | New feature | Enable Notify if Blanket PO Exists. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 41 | There's a need to allow updates to item descriptions on POs even after item creation for business purposes. | New feature | Enable Allow Item Description Update. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 42 | Output POs in a specific document format, "PDF". | New feature | Set Output Format to PDF. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 43 | Control large file attachments on purchasing documents. | New feature | Set Maximum Attachment Size (in MB). | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 44 | Force users to assign a buyer before saving a (PO). | New feature | Enable Enforce Buyer Name. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 45 | Block POs from suppliers that are on hold. | New feature | Enable Enforce Supplier Hold. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 46 | Prevent missing invoice numbers for better audit compliance | New feature | Enable Gapless Invoice Numbering. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 47 | There's a need to make RFQs mandatory before creating POs. | New feature | Enable RFQ Required. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | group shipment | 48 | There's a need to group multiple shipments into a single transaction. | New feature | Enable Group Shipments. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Requisition group | 49 | Group requisition imports by a specific attribute (Item). | New feature | Set Requisition Import Group-By item. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 50 | There's a need to define the source for internal requisitions. | New feature | Set Internal Requisition Order Source to Internal. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
purchasing | Quote warning | 51 | There's a need to warn users before supplier quotes expire a week before. | New feature | Set Quote Warning Delay to 7 days. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Acknowledgment required | 52 | There's a need to Ensure suppliers confirm purchase orders within 2 weeks with a signature. | New feature | Set Acknowledgement Required to signature and define Acknowledgment Lead Time to (14 days). | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Line type | 53 | There's a need define the default line type as goods for POs. | New feature | Set Line Type to "goods". | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Matching rules | 54 | There's a need to Define matching rules with : Invoice- PO- PR- Inspection to validate invoice and submit approval. | New feature | Set Match Approval Level to (4 ways). | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | RFQ Only | 55 | The Giza branch can only request for qutuotions and isn't permitted to make POs. | New feature | Set the checkbox (RFQ Only) in financial options to allowed. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Define supplier | 56 | There is a need to onboard and maintain supplier data. | New feature | Use the Suppliers form to register suppliers, define sites, and business classifications. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Approval hierarchy | 57 | There's a need to make the process of decision-making a hierarchical process. | New feature | Allow the checkbox "Use approval hierarchies" in financial options. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Future periods | 58 | Ensure that users can enter transactions in future accounting periods (1) accounting period in advance. | New feature | Set the future periods to (1) in financial options. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Approval Groups | 59 | Need to ensure that POs are approved by designated individuals before being dispatched. | New feature | Configure Approval Groups and assign them to Position Hierarchies. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Blanket purchase agreement | 60 | Business requires blanket purchase agreements with key vendors to lock pricing terms. | New feature | Set up Blanket Purchase Agreements (BPAs) as needed. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 61 | Users need to raise purchase requisitions that flow into the PO creation. | New feature | Use Requisition Forms in Purchasing and configure AutoCreate functionality for POs. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing |  | 62 | Different types of POs (Standard, BPA) must be supported. | New feature | Enable and configure PO Document Types with appropriate numbering, approvals, and controls. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Purchasing | Unordered Receipt | 63 | There's a need to receive items that don't have POs yet. | New feature | Active the Unordered Receipt on Inventory organization/supplier level/item level. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Order management |  | 64 | There is a need to have an order type for both (returns, orders). | New feature | Define the "Order Category" in transaction types as "Mixed". | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Order management |  | 65 | Ensure orders go through appropriate approval workflows. | New feature | Configure Order Approval Rules in "Approvals’’. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Order management |  | 66 | Automatically price orders based on customer and items. | New feature | Define Pricing Modifiers and Price Lists using Order management application. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Order management |  | 67 | There is a need to enforce a specific price list on specific order types. | New feature | From transaction types, allow (enforce price list) and add the desired price list. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Order management |  | 68 | There is a need to apply discounts on specific order types. | New feature | Define new modifiers (discount modifier). | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Order management |  | 69 | Differentiate between various types of customer orders. | New feature | Define multiple Order Types. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd
Order management |  | 70 | There's a need to use unique document sequences for different order categories. | New feature | Define document sequence categories and attach them to each Order Type. | 2025-03-04 | 2025-03-06 | 2025-03-06 | Closed | Farag - Ashraf- Shimaa- Hegazy- Esraa | Completd